## ICGM測漏治具
|  | 2021 |  | 預估 工作天 | 月 | 6 | [29 empty] | 7 | [30 empty] | 8
序號 | 負責人 | 設計項目 |  |  | 週 | 1 | [5 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 1 | [6 empty] | 2 | [6 empty] | 3
|  |  | 負責人及成員 |  | 日 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Eason | 繪製圖面設計,BOM 表 | 陳思豪/陳宏聞/陳柏帆 | 55
2 | Pegatron | 確認圖面
3 | PUR | 料件請購 | 陳思豪/陳宏聞/陳柏帆 | 35
4 | CNC | CNC 加工 | 陳思豪/陳宏聞/陳柏帆 | 20
5 | ASSY | 組裝，馬達調式 | 陳思豪/陳宏聞/陳柏帆 | 200
6 | Jerry | 程式設計、控制軟體 | 陳思豪/陳宏聞/陳柏帆 | 90

## Lactate Pro Strip Project (2) (hidden)
|  |  |  | 2018 | [19 empty] | 2019 | [47 empty] | 2020 | [47 empty] | 2021
Lactic Pro+ |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12 |  |  |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10 |  |  |  | 11 |  |  |  | 12
|  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Strip | MS1 | 1 | strip design | bar: 8 1 to 10 3
|  | 2 | signal analysis | bar: 10 2 to 11 1
|  | 3 | structure design & sample volume confirm | bar: 11 2 to 1 2; 5 1 to 10 4
|  | 4 | strip signal capture time | bar: 12 2 to 1 4
|  | 5 | algorithm design | bar: 12 4 to 5 1
|  | 6 | formula optimization | bar: 1 3 to 4 2
|  | 7 | curing time analysis | bar: 10 1 to 4 2
|  | 8 | strip stress test | bar: 9 1 to 5 2
|  | 9 | strip real-time test | bar: 5 1 to 10 4
|  | 10 | HCT/temperature parameter design | bar: 5 1 to 5 4; 8 1 to 8 4
|  | 11 | control solution formula optimization | bar: 2 1 to 2 4
|  | 12 | control solution stress test | bar: 2 1 to 3 4
|  | 13 | control solution real-time test | bar: 3 3 to 9 2
|  | 14 | formula preparation verification | bar: 5 3 to 6 2
|  | 15 | strip manufacture process verification | bar: 8 1 to 3 4
|  | 15a | screen printing condition tuning | bar: 12 1 to 1 4
|  | 15b | electrical test jig building | bar: 2 1 to 3 4
|  | 16 | R&D trial run test | bar: 4 1 to 6 4
| MS2 | 17 | BOM＆SOP establish | bar: 3 1 to 3 4
|  | 18 | manufacture OQ | bar: 3 1 to 5 2
|  | 19 | trial run | bar: 5 1 to 7 4
|  | 20 | technical file | bar: 5 1 to 5 4
Meter | MS1 | 1 | ID & review
|  | 2 | ME & soft tooling& review
|  | 4 | Hard tooling
|  | 5 | Strip holder design& tooling
|  | 6 | LCD
|  | 7 | PCBA
|  | 8 | UI & review
|  | 9 | FW
|  | 10 | JIG
|  | 11 | engineering sample & V&V
|  | 12 | EMC
|  | 13 | SOP
|  | 14 | R&D trial production
| MS2 | 15 | manufacture OQ
|  | 16 | TRR
|  | 17 | technical file

## IRB Sample Delivery (simplified (hidden)
|  |  | 2020 | [13 empty] | 2021
Lactic Pro Sample Delivery Schedule |  |  | 10 |  |  |  |  | 11 |  |  |  | 12 |  |  |  |  | 1 |  |  |  | 2 |  |  |  | 3
|  |  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5
Strip | 1 | printing plate building | bar: 10 1 to 10 5
| 2 | spacer punching mold building | bar: 10 4 to 11 4
| 3 | glue spotting OQ condintion trial | bar: 11 4 to 12 5
| 4 | meter layout optimization | bar: 11 1 to 12 3
| 5 | printing plate-plate CV confirmation | bar: 12 3 to 1 1
| 6 | RD sample strip manufacturing | bar: 1 2 to 1 4
| 7 | temperature and HCT function test | bar: 2 3
| 8 | meter PCB lead time | bar: 12 5 to 2 1
| 9 | meter ADC range confirmation | bar: 2 1 to 2 2
| 10 | sample meter QC process | bar: 2 3 to 2 4
| 11 | sample strip accuracy and precision QC process | bar: 2 3 to 2 4

## IRB Sample Delivery (hidden)
|  |  | 2020 | [13 empty] | 2021
Lactic Pro Sample Delivery Schedule |  |  | 10 |  |  |  |  | 11 |  |  |  | 12 |  |  |  |  | 1 |  |  |  | 2 |  |  |  | 3
|  |  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5
Strip | 1 | screen printing pattern confirmaiton | bar: 10 1 to 10 5
| 2 | spacer pattern confirmation | bar: 10 1 to 10 5
| 3 | room temperature curing condtion | bar: 10 4 to 11 4
| 4 | gluing condintion optimization | bar: 11 4 to 12 5
| 5 | meter ADC signal confirmation | bar: 11 1 to 12 3
| 6 | blood standard preparation SOP setup | bar: 12 1 to 12 2
| 7 | formula CV and stability confirmation | bar: 12 1 to 1 1
| 8 | printing plate-plate CV confirmation | bar: 12 3 to 1 1
| 9 | sample strip glue spotting process | bar: 1 2
| 10 | sample strip curing and package process | bar: 1 3
| 11 | temperature and HCT function test | bar: 1 4 to 2 1
| 12 | meter ADC range confirmation | bar: 2 1 to 2 3
| 13 | sample meter QC process | bar: 2 3 to 2 4
| 14 | sample strip accuracy and precision QC process | bar: 2 3 to 2 4
[15 empty] | 隔片測試 | 點膠 | Curing | 溫補 | Meter到/溫補 | 定Code | Accuracy and precision